## Inventory of Available S Consul
Sl. No. | Regions | CLIENT | Month Closed | project status | PERSONNEL | Type | Product | # Days in Contract | Total OMNEX Cost | Mandays Served till April'13 | Amount Billed till April'13 | Balance to be billed in 2013-2014 | Mandays to be spent | Expected Expenses | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | SUM CHECK
1 | Chennai | Alpha | Before April | Y | I | QMS | TS -imp | 32 | 424000 | 14 | -238468 | 238500 | 18 |  | 2013-04-01: 2; 2013-05-01: 2; 2013-06-01: 3; 2013-08-01: 2; 2013-09-01: 2; 2013-10-01: 4; 2013-11-01: 3 | CORRECT
2 | Chennai | Automotive Infotronics | Before April | R | I | QMS | TS -imp | 20 | 360000 | 9 | -197980 | 198000 | 11 |  | 2013-04-01: 0; 2013-05-01: 0 | NOT CORRECT
3 | Chennai | Danfoss | Before April | Y | I | QMS | Ts - trainings | 12 | 216000 | 9 | -50988 | 51000 | 3 |  | 2013-04-01: 3; 2013-05-01: 0 | CORRECT
4 | Chennai | Poclain | 2013-04-01 | R | I | QMS | Supplier improvement | 92 | 1483500 | 16 | -1236267 | 1236359 | 76 | 152000 | 16 | 21 | 24 | 9 | 0 | 0 | 0 | 0 |  |  |  |  | NOT CORRECT
5 | Chennai | klt - halol | Before April | G | I | QMS | nc closure | 4 | 72000 | 4 | 72000 | 0 | 0 |  | 2013-04-01: 4; 2013-05-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0; 2013-11-01: 0 | NOT CORRECT
6 | Chennai | Titan | Before April | G | I | QMS | BPR | 40 | 600000 | 15 | -374960 | 375000 | 25 |  | 3 | 0 | 2 | 4 | 7 | 4 | 1 | 2 | 2 |  |  |  | CORRECT
7 | Chennai | KLT - SA | Before April | G | I | QMS | TS Q1 |  |  |  | -1017225 | 1017225 | 55 |  | 2013-04-01: 0; 2013-05-01: 14; 2013-06-01: 4 | NOT CORRECT
8 | Chennai | AAM | 2013-2014 | G | I | QMS | IA TS | 2 | 34000 | 2 | 34000 | 0 | 0 |  | 2013-04-01: 2; 2013-05-01: 0; 2013-06-01: 0 | NOT CORRECT
9 | Chennai | OET | 2013-2014 | G | I | QMS | LA TS | 5 | 133000 | 5 | 133000 | 0 | 0 |  | 2013-04-01: 5; 2013-05-01: 0 | NOT CORRECT
10 | Chennai | OET | 2013-2014 | G | I | QMS | APQP | 3 | 25000 | 3 | 25000 | 0 | 0 |  | 2013-05-01: 3 | NOT CORRECT
11 | Chennai | Salcomp | Before April | G | O | Lean | Lean | 72 | 2050000 | 2 | -1850622.3 | 1850694.3 | 70 |  | 2 | 3 | 3 | 0 | 5 | 3 | 2 | 3 | 3 | 5 | 3 | 3 | NOT CORRECT
12 | Chennai | al-deer | 2013-2014 | Y | I | QMS | core tool | 7 | 126000 |  | -125993 | 126000 | 7 |  | 2013-09-01: 2; 2013-11-01: 2; 2013-12-01: 3 | CORRECT
13 | Chennai | Gilbarco | 2013-10-01 | Y | I | QMS | core tool | 4 | 72000 |  | -71996 | 72000 | 4 |  | 2013-10-01: 2; 2013-11-01: 2 | CORRECT
14 | Chennai | SFL - pondy | 2013-06-01 | Y | I | QMS | core tool | 9 | 144000 |  | -143991 | 144000 | 9 |  | 2013-06-01: 2; 2013-09-01: 3; 2013-10-01: 2; 2013-11-01: 2 | CORRECT
15 | Chennai | Diamler | 2013-06-01 | G | I | QMS | dfmea | 2 | 40000 |  | -39998 | 40000 | 2 |  | 2013-06-01: 2 | CORRECT
16 | Chennai | Visteon climate | 2013-2014 | G | I | Lean | TPM - DA | 4 | 80000 | 4 | 80000 |  | 0 | [13 empty] | CORRECT
17 | Chennai | ford-thailand | 2013-07-01 | Y | O | QMS | Trainings | 15 |  |  |  |  | 15 |  | 2013-11-01: 15 | CORRECT
18 | Chennai | Ford - STA -july | 2013-07-01 | Y | I | QMS | Trainings | 15 | 837975 |  |  |  | 15 |  | 2013-10-01: 15 | CORRECT
19 | Chennai | Visteon - | 2013-08-01 | Y | I | QMS | IA EMS OSHAS | 4 | 66000 |  | 66000 |  | 4 |  | 2013-08-01: 1; 2013-09-01: 2 | NOT CORRECT
20 | Chennai | Titan | 2013-2014 | G | I | QMS | IA EMS OSHAS | 3 | 49500 | 3 | 49500 |  | 0 | [13 empty] | CORRECT
21 | Chennai | poclain ext cost | 2013-04-01 | R | I | QMS | Supplier improvement | 30 | 105000 | 9 |  | 105000 | 21 | [13 empty] | NOT CORRECT
22 | Chennai | Visteon | 2013-03-01 | G | O | hcd | supervisory develop | 2 | 40000 | 2 |  |  | 0 | [13 empty] | CORRECT
23 | Chennai | Groupo -july | 2013-07-01 | G | I | QMS | EMS - Legal | 1 | 17000 | 1 | 17000 |  | 0 | [13 empty] | CORRECT
24 | Chennai | Bekart - july | 2013-07-01 | G | I | QMS | TS - implimentaton | 24 | 384000 | 0 |  | 384000 | 24 |  |  |  |  | 1 | 2 | 5 | 5 | 4 | 3 | 2 | 2 |  | CORRECT
25 | Chennai | APPG - | 2013-11-01 | G | I | QMS | RCA | 3 | 75000 | 0 |  | 75000 | 3 |  | 2013-11-01: 3 | CORRECT
26 | Chennai | Turbo energy july | 2013-07-01 | G | I | QMS | APQP | 2 | 36000 | 0 |  | 36000 | 2 |  | 2013-08-01: 2 | CORRECT
27 | Chennai | OET - LAT | 2013-08-01 | G | I | QMS | IMS | 5 |  | 0 |  |  | 5 |  | 2013-08-01: 5 | CORRECT
28 | Chennai | OET | 2013-10-01 | R | I |  | DOE | 2 |  | 0 |  |  | 2 |  | 2013-10-01: 2 | CORRECT
29 | Chennai | Bekart | 2013-08-01 | G | I | QMS | core tool | 7 | 119000 | 0 |  |  | 7 |  | 2013-08-01: 1; 2013-09-01: 3; 2013-10-01: 2; 2013-11-01: 1 | CORRECT
30 | Chennai | C P Acqua | 2013-08-01 | G | I | QMS | IA - 9001 | 2 | 36000 | 0 |  |  | 2 |  | 2013-08-01: 2 | CORRECT
31 | Chennai | Visteon Tech | 2013-2014 | G | I | QMS | Process imp | [19 empty] | CORRECT
32 | Chennai | Visteon HVCC - | 2013-10-01 | G | I | Lean | TPM Imp | 40 | 920000 | 0 | 0 | 920000 | 40 |  | 2013-10-01: 2 | NOT CORRECT
33 | Chennai | TVS Credit | 2013-2014 | G | O | Lean | LSS | [19 empty] | CORRECT
34 | Chennai | STML Pondy | 2013-2014 | G | I | QMS | TS - implimentaton | [19 empty] | CORRECT
35 | Chennai | Panasonic Appliances | 2013-09-01 | G | I | QMS | IA ISO 9001 2008 | 3 | 51000 | 0 | 0 | 51000 | 3 |  | 2013-09-01: 2; 2013-10-01: 1 | CORRECT
36 | Chennai | C P Aqua | 2013-09-01 | G | I | QMS | Awareness on OHSAS 18001 | 1 | 18000 | 0 | 0 | 18000 | 1 | [13 empty] | CORRECT | bar: 2013-09-01
37 | Chennai | Turbo Energy | 2013-09-01 | G | I | QMS | PPAP | 1 | 18000 | 0 | 0 | 18000 | 1 | [13 empty] | CORRECT | bar: 2013-09-01
38 | Chennai | CP Aqua | 2013-09-01 | G | I | QMS | Awareness OHSAS | 1 | 18000 | 0 | 0 | 18000 | 1 | [13 empty] | CORRECT | bar: 2013-09-01
39 | Chennai | Visteon | 2013-09-01 | G | I | QMS | IA OHSAS | 2 |  |  |  |  | 2 |  | 2013-09-01: 2 | CORRECT
40 | Chennai | C P Aqua | 2013-10-01 | G | I | QMS | IA OHSAS 18001 | 2 | 18000 | 0 | 0 | 36000 | 2 |  | 2013-10-01: 2 | CORRECT
41 | Chennai | Titan | 2013-10-01 | G | I | EMS | EMS | 1 | 15000 | 0 | 0 | 15000 | 1 | [13 empty] | CORRECT | bar: 2013-10-01
42 | Chennai | Accurate Products | 2013-11-01 | G | I | VDA | IA - VDA 6.3 | 3 | 60000 | 0 | 0 | 60000 | 3 |  | 2013-11-01: 3 | CORRECT
43 | Chennai | Gilbarco Veedor - Mumbai | 2013-11-01 | G | I | QMS | IA - ISO 9001 | 2 | 36000 | 0 | 0 | 36000 | 2 |  | 2013-11-01: 2 | CORRECT
44 | Chennai | OET | 2013-11-01 | G | I | OET | IA /TS 16949 | 2 | 36500 | 0 | 0 | 36500 | 2 |  | 2013-11-01: 2 | CORRECT
45 | Chennai | vistion Interior chennai | 2013-04-01 | G | O | Lean | Lean | 72 | 1575000 | 17 | 371875 | 1203125 | 55 |  | 6 | 0 |  |  | 2 | 3 | 0 | 3 | 3 | 3 | 3 |  | NOT CORRECT
46 | Chennai | vistion electronics chennai | 2013-04-01 | G | O | Lean | Lean | 72 | 1575000 | 14 | 306250 | 1268750 | 58 |  | 3 | 0 |  |  |  | 3 | 0 | 3 | 3 | 3 | 3 |  | NOT CORRECT
47 | Chennai | Visteon climate | 2013-06-01 | G | I | TPM | Lean | 4 | 80000 | 4 | 80000 |  | 0 |  | 2013-06-01: 4 | NOT CORRECT
48 | Chennai | Visteon HVCC - | 2013-09-01 | G | I | TPM | tpm Implemntation | 40 | 920000 | 0 | 0 | 920000 | 40 |  | 2013-10-01: 2; 2013-11-01: 3; 2013-12-01: 3; 2014-01-01: 3; 2014-02-01: 3; 2014-03-01: 3 | NOT CORRECT
49 | Chennai | Simpsons | 2013-11-01 | G | I | QMS | core tool | 5 | 84000 | 0 | 0 | 84000 | 2 |  | 2013-11-01: 1; 2013-12-01: 1; 2014-01-01: 2; 2014-02-01: 1 | NOT CORRECT
50 | Chennai | C P Aqua | 2013-11-01 | G | I | QMS | IA OHSAS 18001 -(2) | 2 | 36000 | 0 | 0 | 36000 | 2 |  | 2013-11-01: 2 | CORRECT
51 | Chennai | OET | 2013-11-01 | G | I | OET | IMS - Lead Auditor | 5 | 58000 | 0 | 0 | 58000 | 5 |  | 2013-11-01: 5 | CORRECT
52 | Pune | Supreme Ind |  | G | I | QMS | Training contract | 60 | 840000 | 35 | 490000 | 350000 | 25 |  | 2013-06-01: 1; 2013-11-01: 4; 2013-12-01: 4; 2014-01-01: 4; 2014-02-01: 4; 2014-03-01: 4 | NOT CORRECT
53 | Pune | Maflow |  | G | I | QMS | TS & 14k Implementation | 45 | 675000 | 5 | 120000 | 555000 | 40 |  | 5 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 4 | 3 |  | CORRECT
54 | Pune | SKF |  | G | I | QMS | GPS-GT (5 batches) | 10 | 400000 | 6 | 240000 | 160000 | 4 |  | 2013-04-01: 2; 2013-12-01: 2 | CORRECT
55 | Pune | TML ERC |  | G | I | QMS | EPS 8D | 120 | 1620000 | 20 | 270000 | 1350000 | 100 |  | 10 | 8 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 10 | 10 | 10 | CORRECT
56 | Pune | shriganesh Microsys |  | G | I | QMS | TS implementation | 30 | 360000 | 10 | 50000 | 310000 | 20 |  | 3 | 2 | 1 | 5 | 2 | 4 | 0 | 2 | 2 | 4 | 4 | 2 | NOT CORRECT
57 | Pune | Nippon |  | G | I | QMS | QMS & EMS implementation | 35 | 450000 | 3 | 90000 | 360000 | 32 |  | 2 | 2 |  | 3 | 5 |  | 4 | 5 | 5 | 3 | 3 |  | CORRECT
58 | Pune | INA |  | G | I | QMS | QMS strengthening | 40 | 600000 | 0 | 0 | 600000 | 40 |  | 0 | 3 | 7 | 6 | 7 | 6 | 4 | 4 | 8 | 8 | 8 | 8 | NOT CORRECT
59 | Pune | Rotex |  | G | I | QMS | TS Implementation | 49 | 472500 | 0 | 0 | 473500 | 49 |  | 2 | 6 |  | 2 |  | 1 | 5 | 0 | 3 | 3 | 3 | 3 | NOT CORRECT
60 | Pune | Visteonlss |  | Y | O | Lean | LSS | 70 | 1600000 | 18 | 414000 | 1186000 | 24 |  | 2013-06-01: 4; 2013-11-01: 5; 2014-02-01: 4 | NOT CORRECT
61 | Pune | TLC |  | Y | I | QMS | Various training | [19 empty] | CORRECT
62 | Pune | Grandpoly |  | Y | I | QMS | TS implementation | 62 | 530000 | 22 | 278000 | 252000 | 42 |  | 8 | 4 |  | 4 |  | 3 | 2 | 0 | 4 | 4 | 4 | 4 | NOT CORRECT
63 | Pune | Raychem |  | G | I | Lean | Six Sigma GB | 28 | 613000 | 5 | 104000 | 509000 | 23 |  | 2013-07-01: 3; 2013-10-01: 3; 2013-11-01: 2; 2013-12-01: 3; 2014-01-01: 3; 2014-02-01: 3; 2014-03-01: 3 | NOT CORRECT
64 | Pune | SETCO |  | G | I | QMS | Training | 140 | 2021000 | 0 | 0 | 2021000 | 140 |  |  |  | 4 | 12 | 2 | 12 | 18 | 13 | 15 | 15 | 15 | 15 | NOT CORRECT
65 | Pune | IAI Joinflex |  | G | I | QMS | Training contract | 25 | 400000 | 2 | 32000 | 368000 | 23 |  | 2013-04-01: 2; 2013-10-01: 3; 2013-11-01: 0; 2013-12-01: 2; 2014-01-01: 2; 2014-02-01: 2 | NOT CORRECT
66 | Pune | ZF |  | G | I | QMS | Trainings | 60 | 900000 | 0 | 0 | 900000 | 60 |  |  | 3 | 3 | 6 | 3 | 3 | 6 | 2 | 2 | 6 | 2 | 2 | NOT CORRECT
67 | Pune | Force motors |  | G | I | QMS | Training contract | 28 | 420000 | 0 | 0 | 750000 | 28 |  | 0 | 0 | 0 | 0 |  | 4 | 4 | 9 | 9 | 9 | 9 | 9 | NOT CORRECT
68 | Pune | Mahindra navistar |  | G | I | QMS | TS AUDit | 10 | 136000 |  |  | 136000 | 10 |  | 2013-05-01: 6; 2013-10-01: 4; 2013-11-01: 4; 2013-12-01: 4 | NOT CORRECT
69 | Pune | Flowmetalics |  | G | I | QMS | trainings | 12 | 180000 |  |  | 180000 | 12 |  | 2013-06-01: 6; 2013-07-01: 2; 2013-09-01: 2; 2013-10-01: 2; 2013-11-01: 2; 2013-12-01: 2 | NOT CORRECT
70 | Pune | HEG LTD |  | G | I | Lean | LSS OVERVIEW trg | 1 | 20000 |  |  | 20000 | 1 | [13 empty] | CORRECT | bar: 2013-07-01
71 | Pune | Philps |  | G | I | QMS | MSA-SPC | 3 | 50000 |  |  | 50000 | 3 |  | 2013-06-01: 3 | CORRECT
72 | Pune | SJP Ultrasonic |  | G | I | QMS | GD&T | 3 | 55000 |  |  | 55000 | 3 |  | 2013-07-01: 3 | CORRECT
73 | Pune | Magneti |  | G | I | QMS | APQP | 3 | 50000 |  |  | 50000 | 3 |  | 2013-08-01: 3 | CORRECT
74 | Pune | Visteon |  | G | I | QMS | MSA & QC | 3 | 50000 |  |  | 50000 | 3 |  | 2013-07-01: 3 | CORRECT
75 | Pune | Bekeart |  | G | I | QMS | IMS IQA | 4 | 80000 |  |  | 80000 | 4 |  | 2013-09-01: 4 | CORRECT
76 | Pune | Harsha Eng |  | G | I | QMS | FMEA | 2 | 30000 |  |  | 30000 | 2 |  | 2013-07-01: 2 | CORRECT
77 | Pune | Skoda |  | G | I | QMS | [6 empty] | 147 |  | 2013-08-01: 26; 2013-09-01: 35; 2013-10-01: 21; 2013-11-01: 25; 2013-12-01: 19; 2014-01-01: 19 | NOT CORRECT
78 | Pune | Yengfeng Visteon |  | G | I | QMS | MSA/SPC Refresher | 2 | 30000 |  |  | 30000 | 2 |  | 2013-08-01: 2 | CORRECT
79 | Pune | Visteon |  | G | I | QMS | QC trg & Implementation | 18 | 300000 |  |  | 300000 | 18 | [5 empty] | 2 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | NOT CORRECT
80 | Pune | Minda |  | G | I | QMS | SPC | 2 | 30000 |  |  | 30000 | 2 |  | 2013-09-01: 2 | CORRECT
81 | Pune | Furecia |  | G | I | QMS | VDA & TS IQA | 6 | 80000 |  |  | 80000 | 6 |  | 2013-09-01: 3; 2013-10-01: 3; 2013-11-01: 3; 2013-12-01: 3 | NOT CORRECT
82 | Pune | Eicher |  | G | I | QMS | GD&T | 2 | 50000 |  |  | 50000 | 2 |  | 2013-08-01: 2 | CORRECT
83 | Pune | Kalyani |  | G | I | QMS | Q1 Assessment | 2 | 27000 |  |  | 27000 | 2 |  | 2013-08-01: 2 | CORRECT
84 | Pune | Mercedes |  | G | I | QMS |  | 2 | 40000 |  |  | 40000 | 2 |  | 2013-07-01: 2 | CORRECT
85 | Pune | Econ Packaging |  | G | I | QMS | Assessment | 1 | 20000 |  |  | 20000 | 1 | [13 empty] | CORRECT | bar: 2013-07-01
86 | Pune | HYVA |  | G | I | QMS | Core tools | 8 | 160000 |  |  | 160000 | 8 |  | 2013-09-01: 3; 2013-10-01: 3; 2013-11-01: 3; 2013-12-01: 2; 2014-01-01: 3 | NOT CORRECT
87 | Pune | Maflow |  | G | O | QMS | Soft Skills | 6 | 100000 |  |  | 100000 | 6 |  | 2013-10-01: 1; 2013-11-01: 2; 2013-12-01: 2; 2014-01-01: 1; 2014-02-01: 1; 2014-03-01: 1 | NOT CORRECT
88 | Pune | Eicher |  | G | I | QMS |  | 1 | 13500 |  |  | 13500 | 1 | [13 empty] | CORRECT | bar: 2013-09-01
89 | Pune | Minda corporatation |  | G | I | QMS | SPC | 2 | 30000 |  |  | 30000 | 2 |  | 2013-10-01: 2 | CORRECT
90 | Pune | Lear |  | G | I | QMS | ISO17025 IQA | 4 | 85000 |  |  | 85000 | 4 |  | 2013-10-01: 4 | CORRECT
91 | Pune | Setco |  | G | I | QMS | trg evaluation |  | 39000 |  |  | 39000 | 3 |  | 2013-10-01: 3 | CORRECT
92 | Pune | Excelcontrol |  | G | I | QMS | EMS implementation |  | 300000 |  |  | 300000 |  |  | 2013-11-01: 4; 2013-12-01: 4; 2014-01-01: 4; 2014-02-01: 4; 2014-03-01: 4 | NOT CORRECT
93 | Pune | TML |  | G | I | QMS | SQE trg | 132 | 1980000 |  | 132 | 1980000 |  |  | 2013-11-01: 45; 2013-12-01: 40; 2014-01-01: 40; 2014-02-01: 40; 2014-03-01: 12 | NOT CORRECT
94 | Pune | FAG |  | G | O | QMS | Soft Skill trgs |  | 80000 |  |  | 80000 |  |  | 2013-10-01: 2; 2013-11-01: 2 | NOT CORRECT
95 | Pune | Setco Uttarakhand |  | G | I | QMS | Trainings |  | 96000 |  |  | 96000 |  |  | 2013-10-01: 2; 2013-11-01: 2; 2013-12-01: 2 | NOT CORRECT
96 | Pune | Samarath |  | G | I | QMS | ISO9001 Implementation | [7 empty] | 2013-10-01: 1; 2013-11-01: 40; 2013-12-01: 2; 2014-01-01: 2; 2014-02-01: 2; 2014-03-01: 2 | NOT CORRECT
97 | Pune | Eicher |  | G | I | QMS | FMEA workshop | 3 | 40500 |  |  | 40500 | 3 |  | 2013-10-01: 3 | CORRECT
98 | Pune | FAG |  | G | I | QMS | TS u/s trg |  | 40000 |  |  | 40000 |  |  | 2013-10-01: 2 | NOT CORRECT
99 | Pune | MPCB |  | G | I | QMS | ISO9001 & OHSAS18001 Implementation |  | 3932000 |  |  | 3932000 |  |  | 2013-11-01: 10; 2013-12-01: 40; 2014-01-01: 40; 2014-02-01: 30 | NOT CORRECT
100 | Pune | johndeere |  | G | O | HCD | SSP | 8 | 160000 | 2 | 40000 | 120000 | 6 |  | 2013-04-01: 0; 2013-05-01: 4; 2013-06-01: 2 | CORRECT
101 | Pune | johndeere |  | G | O | HCD | SSP | 10 | 200000 |  |  | 200000 | 10 |  | 2013-07-01: 6; 2013-08-01: 2; 2013-09-01: 2 | CORRECT
102 | Delhi | Continental Engines | 2012-2013 | G | I | Lean | SS GB Implementation | 53 | 470000 | 49 | 368000 | 102000 | 4 |  | 2013-04-01: 3; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 1 | CORRECT
103 | Delhi | IMI Norgren | 2012-2013 | G | I | QMS | Training contract-QMS | 7 | 94500 | 3 | 40500 | 54000 | 4 |  | 2013-04-01: 0; 2013-05-01: 1; 2013-06-01: 0; 2013-07-01: 2; 2013-08-01: 1 | CORRECT
104 | Delhi | Sigma Vibracoustiv | 2012-2013 | G | I | QMS | Training contract-QMS | 4 | 60000 | 2 | 30000 | 30000 | 2 |  | 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 2 | CORRECT
105 | Delhi | Tata Steel growth Shop | 2012-2013 | G | I | QMS | MSA Implementation | 14 | 268000 | 12 | 230000 | 38000 | 2 |  | 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 2 | CORRECT
106 | Delhi | JCB | 2013-04-01 | G | I | QMS | Training contract-QMS | 40 | 720000 | 0 | 0 | 720000 | 40 |  | 2 | 3 | 3 | 3 | 5 | 4 | 6 | 6 | 8 |  |  |  | CORRECT
107 | Delhi | SPM Autocomp,Pune | 2013-04-01 | G | I | QMS | Training contract-QMS | 14 | 182000 | 0 | 91000 | 0 | 14 |  | 2013-04-01: 7; 2013-05-01: 1; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 2; 2013-09-01: 4 | CORRECT
108 | Delhi | MACE | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-04-01: 2 | CORRECT
109 | Delhi | ST MICRO,DFMEA | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 42000 | 0 | 0 | 42000 | 2 |  | 2013-04-01: 2 | CORRECT
110 | Delhi | ALP,Nishikawa-TQM | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 36000 | 0 | 0 | 36000 | 2 |  | 2013-04-01: 2 | CORRECT
111 | Delhi | Eco Cat-DOE | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 50000 | 0 | 0 | 50000 | 2 |  | 2013-04-01: 2 | CORRECT
112 | Delhi | JCB-DFMEA | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 43000 | 0 | 0 | 43000 | 2 |  | 2013-04-01: 2 | CORRECT
113 | Delhi | Federal mogul | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 28000 | 0 | 0 | 28000 | 2 |  | 2013-04-01: 2 | CORRECT
114 | Delhi | Lifelng,Haridwar | 2013-04-01 | G | I |  | Training contract-QMS | 4 | 60000 | 0 | 0 |  | 4 |  | 2013-10-01: 2; 2013-11-01: 2 | CORRECT
115 | Delhi | OMB Saleri | 2013-04-01 | G | I | QMS | Training contract-QMS | 2 | 15000 | 0 | 0 | 15000 | 2 |  | 2013-04-01: 2 | CORRECT
116 | Delhi | Visteon Climate | 2013-04-01 | G | O | QMS | Lean Impl | 5 | 125000 | 0 | 0 | 125000 | 5 |  | 2013-04-01: 5 | CORRECT
117 | Delhi | Shriram Pistons,Biwadi | 2013-05-01 | G | I | QMS | Training contract-QMS | 16 | 250000 | 0 | 0 | 250000 | 16 |  | 0 | 0 | 3 | 3 | 4 | 4 | 1 | 1 |  |  |  |  | CORRECT
118 | Delhi | Visteon Climate,System | 2013-05-01 | G | I | QMS | Training contract-QMS | 9 | 183000 | 0 |  | 183000 | 9 |  | 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 1; 2013-08-01: 4; 2013-09-01: 2; 2013-10-01: 2 | CORRECT
119 | Delhi | Eco Cat,Faridabad | 2013-05-01 | G | I | QMS | Training contract-QMS | 3 | 55000 | 0 | 0 | 55000 | 3 |  | 2013-05-01: 3 | CORRECT
120 | Delhi | JCB,Faridabad | 2013-05-01 | G | I | QMS | Training contract-QMS | 2 | 43000 | 0 | 0 | 43000 | 2 |  | 2013-05-01: 2 | CORRECT
121 | Delhi | Sanden Vikas | 2013-05-01 | G | I | QMS | Training contract-QMS | 2 | 30000 |  |  | 30000 | 2 | [13 empty] | CORRECT | bar: 2013-06-01 to 2013-07-01
122 | Delhi | Talbros,Faridabad | 2013-05-01 | G | I | QMS | Training contract-QMS | 2 | 30000 |  |  | 30000 | 2 |  | 2013-06-01: 0; 2013-07-01: 2 | CORRECT
123 | Delhi | BGL,Faridabad | 2013-05-01 | G | I | QMS | Training contract-QMS | 4 | 60000 | 0 | 0 | 60000 | 4 |  | 2013-05-01: 2; 2013-06-01: 2 | CORRECT
124 | Delhi | Federal Mogul,Bhiwadi | 2013-05-01 | G | I | QMS | Training contract-QMS | 1 | 15000 | 0 | 0 | 15000 | 1 | [13 empty] | CORRECT | bar: 2013-05-01
125 | Delhi | Mate,Noida | 2013-05-01 | G | I | QMS | Training contract-QMS | 3 | 39750 | 0 | 0 | 39750 | 3 |  | 2013-05-01: 2; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 1 | CORRECT
126 | Delhi | Telleborg,Noida | 2013-05-01 | G | I | QMS | Training contract-QMS | 1 | 15500 | 0 | 0 | 15500 | 1 | [13 empty] | CORRECT | bar: 2013-05-01
127 | Delhi | ALP Nishikawa | 2013-05-01 | G | I | QMS | Training contract-QMS | 2 | 26000 | 0 | 0 | 26000 | 2 |  | 2013-05-01: 2 | CORRECT
128 | Delhi | JCB,Faridabad | 2013-05-01 | G | I | QMS | Training contract-QMS | 1 | 19000 |  |  | 19000 | 1 | [13 empty] | CORRECT | bar: 2013-06-01
129 | Delhi | Caparo fasteners | 2013-05-01 | G | I | QMS | Training contract-QMS | 1 | 13500 |  |  | 13500 | 1 | [13 empty] | CORRECT | bar: 2013-06-01
130 | Delhi | Mace | 2013-05-01 | G | I | QMS | Training contract-QMS | 2 | 30000 |  |  | 30000 | 2 |  | 2013-06-01: 2 | CORRECT
131 | Delhi | AMTEK TEKFOR | 2013-06-01 | G | I | QMS | OET-LA TS & MSA | 7 | 118000 | 0 | 0 | 118000 | 7 |  | 2013-06-01: 5; 2013-07-01: 0; 2013-08-01: 2 | CORRECT
132 | Delhi | AMTEK TEKFOR | 2013-06-01 | G | I | QMS | IQA ISO/TS | 3 | 45000 | 0 | 0 | 45000 | 3 |  | 2013-06-01: 3 | CORRECT
133 | Delhi | AMTEK TEKFOR | 2013-06-01 | G | I | QMS | Handholding&Consultancy | 13 | 130000 | 0 | 0 | 130000 | 13 |  | 2013-07-01: 13 | CORRECT
134 | Delhi | JTEKT SONA | 2013-06-01 | G | I | QMS | Training contract-QMS | 4 | 75000 | 0 | 0 | 75000 | 4 |  | 2013-06-01: 2; 2013-07-01: 2 | CORRECT
135 | Delhi | Ericsson,Jaipur | 2013-06-01 | G | I | QMS | MSA&SPC | 3 | 48000 | 0 | 0 | 48000 | 3 |  | 2013-07-01: 0; 2013-08-01: 3 | CORRECT
136 | Delhi | MSIL,Gurgaon | 2013-06-01 | G | O | hcd | Behavioral Training | 2 | 67000 | 0 | 0 | 67000 | 2 |  | 2013-07-01: 0; 2013-08-01: 2 | CORRECT
137 | Delhi | Zavenir,Binola | 2013-06-01 | G | I | QMS | IQA IMS | 3 | 42000 | 0 | 0 | 42000 | 3 |  | 2013-07-01: 3 | CORRECT
138 | Delhi | TML,Jamshedpur | 2013-06-01 | G | I | QMS | APQP,PPAP& G8D | 4 | 80000 | 0 | 0 | 80000 | 4 |  | 2013-08-01: 2; 2013-09-01: 2 | CORRECT
139 | Delhi | Sanden Vikas | 2013-06-01 | G | I | QMS | OEE,G8D | 3 | 45000 | 0 | 0 | 45000 | 3 |  | 2013-08-01: 1; 2013-09-01: 2 | CORRECT
140 | Delhi | Talbros,Gurgaon | 2013-06-01 | G | I | QMS | 7 QC Tools | 1 | 13000 | 0 | 0 | 13000 | 1 | [13 empty] | CORRECT | bar: 2013-07-01
141 | Delhi | Federal Mogul | 2013-06-01 | G | I | QMS | MSA | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-09-01: 2 | CORRECT
142 | Delhi | ALP Nishikawa,Lalru | 2013-07-01 | G | I | QMS | QMS-SPC | 2 | 26000 | 0 | 0 | 26000 | 2 |  | 2013-07-01: 2 | CORRECT
143 | Delhi | ALP Nishikawa,Gurgaon | 2013-07-01 | G | I | QMS | QMS-Quality Circle | 1 | 13000 | 0 | 0 | 13000 | 1 | [13 empty] | CORRECT | bar: 2013-07-01
144 | Delhi | Mahle,Gurgaon | 2013-07-01 | G | I | QMS | 7 QC Tools | 1 | 15000 | 0 | 0 | 15000 | 1 | [13 empty] | CORRECT | bar: 2013-07-01
145 | Delhi | Mahle,Parwanoo | 2013-07-01 | G | I | QMS | 7 QC Tools,Cost Of Quality | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-08-01: 2 | CORRECT
146 | Delhi | Amtek,Pune | 2013-07-01 | G | I | QMS | IQA ISO/TS 16949 | 3 | 42000 | 0 | 0 | 42000 | 3 |  | 2013-08-01: 3 | CORRECT
147 | Delhi | Subros,Manesar | 2013-07-01 | G | I | QMS | IQA EHS | 3 | 51000 | 0 | 0 | 51000 | 3 |  | 2013-09-01: 3 | CORRECT
148 | Delhi | Subros,Pune | 2013-07-01 | G | I | QMS | IQA EHS | 3 | 51000 | 0 | 0 | 51000 | 3 |  | 2013-08-01: 3 | CORRECT
149 | Delhi | MSIL,Gurgaon | 2013-07-01 | G | I | QMS | PFMEA | 2 | 34000 | 0 | 0 | 34000 | 2 |  | 2013-08-01: 2 | CORRECT
150 | Delhi | DR.Reddy Pathlabs,HYD | 2013-07-01 | G | I | QMS | Root Cause Analysis | 2 | 45000 | 0 | 0 | 45000 | 2 |  | 2013-08-01: 2 | CORRECT
151 | Delhi | Mahle,Parwanoo | 2013-08-01 | G | I | QMS | Kaizen&Poka yoke,TPM,Vendor System Audit | 4 | 65000 | 0 | 0 | 65000 | 4 |  | 2013-09-01: 4 | CORRECT
152 | Delhi | Mate,Chennai | 2013-08-01 | G | I | QMS | APQP PPAP | 2 | 26500 | 0 | 0 | 26500 | 2 |  | 2013-09-01: 2 | CORRECT
153 | Delhi | Amtek,Pune | 2013-08-01 | G | I | QMS | PFMEA;APQP PPAP | 4 | 60000 | 0 | 0 | 60000 | 4 |  | 2013-09-01: 2; 2013-10-01: 2 | CORRECT
154 | Delhi | Continental Auto, Manesr | 2013-08-01 | G | I | QMS | APQP PPAP,IQA TS,DOE | 6 | 110000 | 0 | 0 | 110000 | 6 |  | 2013-09-01: 2; 2013-10-01: 2; 2013-11-01: 2 | CORRECT
155 | Delhi | Continental Auto, Manesr | 2013-08-01 | G | I | QMS | TPM,GD&T | 4 | 91000 | 0 | 0 | 91000 | 4 |  | 2013-12-01: 2; 2014-01-01: 2 | CORRECT
156 | Delhi | SPM Autocomp,Pune | 2013-08-01 | G | I | QMS | IMDS | 1 | 23500 | 0 | 0 | 23500 | 1 | [13 empty] | CORRECT | bar: 2013-10-01
157 | Delhi | Hamdard Laboratories | 2013-09-01 | G | I | QMS | Soft Skill | 20 | 3000000 | 0 | 0 | 3000000 | 20 |  | 2013-10-01: 4; 2013-11-01: 6; 2013-12-01: 6; 2014-01-01: 4 | CORRECT
158 | Delhi | Mahle,Gurgaon | 2013-09-01 | G | I | QMS | Supply Chain | 2 | 50000 | 0 | 0 | 50000 | 2 |  | 2013-10-01: 2 | CORRECT
159 | Delhi | Subros,Pune | 2013-09-01 | G | I | QMS | IQA ISO/TS 16949 | 3 | 51000 | 0 | 0 | 51000 | 3 |  | 2013-10-01: 3 | CORRECT
160 | Delhi | Federal Mogul,Bhiwadi | 2013-09-01 | G | I | QMS | IQA EHS | 3 | 45000 | 0 | 0 | 45000 | 3 |  | 2013-10-01: 3 | CORRECT
161 | Delhi | Jtekt Sona, Bawal | 2013-09-01 | G | I | QMS | DOE | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-09-01: 2 | CORRECT
162 | Delhi | Mate, | 2013-09-01 | G | I | QMS | SPC | 2 | 26000 | 0 | 0 | 26000 | 2 |  | 2013-10-01: 2 | CORRECT
163 | Delhi | ALP Nishikawa | 2013-09-01 | G | I | QMS | SPC & MSA | 4 | 56000 | 0 | 0 | 56000 | 4 |  | 2013-11-01: 2; 2013-12-01: 2 | CORRECT
164 | Delhi | Subros,Noida | 2013-09-01 | G | I | QMS | IQA ISO/TS 16949 | 3 | 51000 | 0 | 0 | 51000 | 3 |  | 2013-12-01: 3 | CORRECT
165 | Delhi | Denso,Manesar | 2013-07-01 | G | O | HCD | Supervisor Development Program(Behavioral) | 5 | 85000 | 0 | 0 | 85000 | 5 |  | 2013-07-01: 0; 2013-08-01: 3; 2013-09-01: 2 | CORRECT
166 | Delhi | Denso,Manesar | 2013-07-01 | G | O | HCD | Train the Trainer(Behavioral) | 2 | 50000 | 0 | 0 | 50000 | 2 |  | 2013-08-01: 2 | CORRECT
167 | Delhi | Treleborg,Noida | 2013-07-01 | G | O | HCD | Leadership Skills | 2 | 45000 | 0 | 0 | 45000 | 2 |  | 2013-09-01: 2 | CORRECT
168 | Delhi | Sanden Vikas,Faridabad | 2013-07-01 | G | O | HCD | Soft Skill | 4 | 90000 | 0 |  | 90000 | 4 |  | 2013-08-01: 2; 2013-09-01: 2 | CORRECT
169 | Delhi | Visteon Climate | 2013-07-01 | G | O | LSS | QMS | 5 | 125000 | 0 | 0 | 125000 | 5 |  | 2013-04-01: 5 | CORRECT
170 | Delhi | Henkel,Chennai | 2013-11-01 | G | I | QMS | Ford Q1 Audit | 2 | 36000 | 0 | 0 | 36000 | 2 |  | 2013-09-01: 2 | CORRECT
171 | Delhi | Denso International | 2013-10-01 | G | O | HCD | Presentation Skills | 2 | 48000 | 0 | 0 | 48000 | 2 |  | 2013-11-01: 2 | CORRECT
172 | Delhi | Mate, | 2013-10-01 | G | I | QMS | Quality Circle,G8D,7QC | 9 | 119250 | 0 | 0 | 119250 | 9 |  | 2013-09-01: 2; 2013-10-01: 4; 2013-11-01: 3 | CORRECT
173 | Delhi | JCB,Faridabad | 2013-10-01 | G | I | QMS | G8D,APQP PPAP | 4 | 74000 | 0 | 0 | 74000 | 4 |  | 2013-11-01: 2; 2013-12-01: 2 | CORRECT
174 | Delhi | Woco Motherson,Noida | 2013-10-01 | G | I | QMS | Awareness ISO/TS,SPC&MSA | 4 | 50000 | 0 | 0 | 50000 | 4 |  | 2013-10-01: 2; 2013-11-01: 2 | CORRECT
175 | Delhi | Shriram Pistons | 2013-10-01 | G | I | QMS | SPC MSA,GD&T | 13 | 235000 | 0 | 0 | 235000 | 13 |  | 2013-12-01: 4; 2014-01-01: 4; 2014-02-01: 5 | CORRECT
176 | Delhi | ALP Nishikawa,lalru | 2013-10-01 | G | I | QMS | SPC | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-11-01: 2; 2013-12-01: 0 | CORRECT
177 | Delhi | Dr Reddy Laboratories | 2013-10-01 | G | I | QMS | RCA | 2 | 45000 | 0 | 0 | 45000 | 2 |  | 2013-12-01: 2 | CORRECT
178 | Delhi | MACE,Gurgaon | 2013-11-01 | G | I | QMS | IQA ISO/TS,IQA EHS,IQA ISO/TS | 6 | 90000 | 0 | 0 | 90000 | 6 |  | 2013-11-01: 2; 2013-12-01: 2; 2014-01-01: 2 | CORRECT
179 | Delhi | JCB,Pune | 2013-11-01 | G | I | QMS | PFMEA | 1 | 16500 | 0 | 0 | 16500 | 1 | [13 empty] | CORRECT | bar: 2013-12-01
180 | Delhi | Jtekt Sona,Bawal | 2013-11-01 | G | I | QMS | 7 QC Tools | 1 | 15000 | 0 | 0 | 15000 | 1 | [13 empty] | CORRECT | bar: 2013-11-01
181 | Delhi | Mate,Chennai+Noida+Bangalore | 2013-11-01 | G | I | QMS | Overview+7 QC+12 steps | 4 | 53000 | 1 | 13250 | 39750 | 3 | [13 empty] | CORRECT | bar: 2013-11-01 to 2014-01-01
182 | Bangalore | TATA MARCOPOLO | 2013-04-01 | G | I | QMS | SIX SIGMA YELLOW BELT | 30 | 600000 | 9 | 120000 | 420000 | 21 |  | 2013-06-01: 3; 2013-07-01: 3; 2013-08-01: 3; 2013-09-01: 3; 2013-12-01: 6; 2014-02-01: 3 | CORRECT
183 | Bangalore | Larsen & toubro Ltd Mys | 2013-04-01 | G | I | QMS | Core tools | 8 | 156000 | 4 | 76000 | 80000 | 4 |  | 2014-01-01: 2; 2014-02-01: 2 | CORRECT
184 | Bangalore | JSW | 2013-06-01 | G | I | QMS | ISO/TS implementation | 72 | 1152000 | 2 | 36000 | 1116000 | 70 |  |  |  |  | 2 | 2 | 8 | 7 | 3 | 8 | 10 | 11 | 13 | NOT CORRECT
185 | Bangalore | FESTO CONTROLS | 2013-08-01 | G | I | QMS | EPS | 7 | 140000 | 0 |  |  | 7 |  | 2014-02-01: 5; 2014-03-01: 2 | CORRECT
186 | Bangalore | FAURECIA | 2013-08-01 | G | I | QMS | Core Tools | 3 | 60000 |  |  |  | 3 |  | 2013-12-01: 3 | CORRECT
187 | Bangalore | Inteva | 2013-09-01 | G | I |  | IQA/TS | 3 | 60000 |  |  |  | 3 |  | 2013-09-01: 3 | CORRECT
188 | Corporate | DLMI |  | G | I | LSS | LSS Implementation | 100 | 2500000 | 8 | 200000 | 2300000 | 92 | 120000 | 8 | 16 | 10 | 10 | 14 | 13 | 4 | 6 | 5 |  |  |  | NOT CORRECT
189 | Corporate | TTR |  | G | I | QMS | SIT | 35 | 700000 | 19 | 70000 | 630000 | 16 | 15000 | 2013-05-01: 4; 2013-06-01: 7; 2013-07-01: 2; 2013-08-01: 1; 2013-09-01: 2 | CORRECT
190 | Corporate | Mahindra composites |  | G | I | QMS | SIT | 35 | 700000 | 19 | 245000 | 455000 | 16 | 15000 | 2013-04-01: 2; 2013-05-01: 2; 2013-06-01: 6; 2013-07-01: 6 | CORRECT
191 | Corporate | ZF |  | G | I | QMS | SIT | 35 | 700000 | 28 | 70000 | 630000 | 7 | 15000 | 2013-04-01: 1; 2013-05-01: 5; 2013-06-01: 1 | CORRECT
192 | Corporate | Bhadve |  | G | I | QMS | SIT | 35 | 700000 | 17 | 70000 | 630000 | 18 | 15000 | 2013-04-01: 5; 2013-05-01: 3; 2013-06-01: 7; 2013-07-01: 0; 2013-08-01: 1 | NOT CORRECT
193 | Corporate | Neosem |  | G | I | QMS | SIT | 35 | 700000 | 13 | 70000 | 630000 | 22 | 15000 | 2013-05-01: 2; 2013-06-01: 7; 2013-07-01: 7; 2013-08-01: 6 | CORRECT
194 | Corporate | CM Smith Machine Shop |  | G | I | QMS | SIT | 35 | 700000 | 23 | 70000 | 630000 | 12 | 15000 | 2013-04-01: 4; 2013-05-01: 3; 2013-06-01: 6; 2013-07-01: 8; 2013-08-01: 2; 2013-09-01: 2 | NOT CORRECT
195 | Corporate | Omax |  | G | I | QMS | SIT | 35 | 700000 | 21 | 70000 | 630000 | 14 | 15000 | 2013-05-01: 5; 2013-06-01: 7; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0 | NOT CORRECT
196 | Corporate | Elforge |  | G | I | QMS | SIT | 35 | 700000 | 22 | 245000 | 455000 | 13 | 15000 | 2013-04-01: 3; 2013-05-01: 2; 2013-06-01: 4; 2013-07-01: 0 | NOT CORRECT
197 | Corporate | IAC |  | G | I | QMS | SIT | 35 | 700000 | 8 | 245000 | 455000 | 27 | 15000 | 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0 | NOT CORRECT
198 | Corporate | Asahi |  | G | I | QMS | SIT | 35 | 700000 | 14 | 70000 | 630000 | 21 | 15000 | 2013-04-01: 4; 2013-05-01: 0; 2013-06-01: 2; 2013-07-01: 0 | NOT CORRECT
199 | Corporate | JBM |  | G | I | QMS | SIT | 35 | 700000 | 11 | 70000 | 630000 | 24 | 15000 | 2013-04-01: 3; 2013-05-01: 1; 2013-06-01: 3; 2013-07-01: 0 | NOT CORRECT
200 | Corporate | Deccan Hydraulics |  | G | I | QMS | SIT | 35 | 700000 | 20 | 70000 | 630000 | 15 | 15000 | 2013-04-01: 2; 2013-05-01: 1; 2013-06-01: 2; 2013-07-01: 0 | NOT CORRECT
201 | Corporate | Machino |  | G | I | QMS | SIT | 35 | 700000 | 16 | 70000 | 630000 | 19 | 15000 | 2013-04-01: 2; 2013-05-01: 4; 2013-06-01: 9; 2013-07-01: 2 | NOT CORRECT
202 | Corporate | CM Smith foundry |  | G | I | QMS | SIT | 35 | 700000 | 0 | 0 | 700000 | 35 | 15000 | 2013-05-01: 1; 2013-06-01: 4; 2013-07-01: 6; 2013-08-01: 4; 2013-09-01: 20 | CORRECT
203 | Corporate | shankar |  | G | I | QMS | Mfg. Excellence | 104 | 1716000 | 6 | 192000 | 1524000 | 98 | 10000 | 10 | 7 |  | 5 | 2 | 4 | 15 | 15 | 15 | 15 | 10 |  | CORRECT
204 | Corporate | KFIL Audit |  | G | I | QMS | [5 empty] | 80000 | 4 |  | 2013-08-01: 4 | CORRECT
205 | Corporate | New Balance |  | G | I | QMS | SPC MSA Vietnam | 4 | 212400 |  |  | 212400 | 4 |  | 2013-07-01: 4 | CORRECT
206 | Corporate | Gokaldas Images-Enamor |  | G | I | QMS | StrategY | 70 |  |  |  |  | 70 |  | 2013-09-01: 4; 2013-10-01: 20; 2013-11-01: 2; 2013-12-01: 5; 2014-01-01: 6; 2014-02-01: 15; 2014-03-01: 18 | CORRECT
207 | Corporate | Gokaldas Images-Enamor |  | G | O | Strat | QMS | 25 |  |  |  |  | 25 |  | 2013-09-01: 3; 2013-10-01: 4; 2013-11-01: 5; 2013-12-01: 5; 2014-01-01: 4; 2014-02-01: 3 | NOT CORRECT
208 | Corporate | New Balance |  | G | O | LSS | LSS Training | 8 | 417600 |  |  | 417600 | 8 |  | 2013-08-01: 4; 2013-10-01: 4 | CORRECT
209 | Corporate | New Balance |  | G | O | LSS | LSS Training | 8 | 613600 |  |  | 613600 | 8 |  | 2013-08-01: 4; 2013-10-01: 4 | CORRECT
210 | Corporate | New Balance |  | G | O | LSS | LSS Training | 8 | 613600 |  |  | 613600 | 8 |  | 2013-08-01: 4; 2013-10-01: 4 | CORRECT
211 | Corporate | New Balance |  | G | O | LSS | LSS Training | 8 | 424800 |  |  | 424800 | 8 |  | 2013-07-01: 4; 2013-10-01: 4 | CORRECT
212 | Corporate | New Balance |  | G | O | QMS | QMS | 4 | 212400 |  |  | 212400 | 4 |  | 2013-08-01: 4 | CORRECT
213 | Corporate | New Balance |  | G | O | QMS | QMS | 4 | 306800 |  |  | 306800 | 4 |  | 2013-07-01: 4 | CORRECT
214 | Corporate | Skoda |  | G | AC | QMS | ISO9001:2008 (ass. consultant) | [5 empty] | 275 |  | 2013-04-01: 67; 2013-05-01: 76; 2013-06-01: 68; 2013-07-01: 68; 2013-08-01: 70; 2013-09-01: 88 | NOT CORRECT
215 | Corporate | shankarAC |  | G | AC | QMS | Mfg. Excellence (AC) | 141 | 846000 | 35 | 315000 | 531000 | 106 | 5000 | 2013-04-01: 39; 2013-05-01: 37; 2013-06-01: 21; 2013-07-01: 8; 2013-08-01: 20; 2013-09-01: 15; 2013-10-01: 7 | NOT CORRECT
216 | Corporate | Gokaldas Images-Enamor |  | G | AC | Strat | Strategicc | [5 empty] | 30 |  | 2013-09-01: 12; 2013-10-01: 11; 2013-11-01: 6; 2013-12-01: 0; 2014-01-01: 1 | CORRECT
217 | Corporate | Siemens |  | G | I | QMS | VDA | 3 | 60000 | 0 | 0 | 60000 | 3 |  | 2013-12-01: 3 | CORRECT
218 | Corporate | Noor Islamic |  | G | I | QMS |  | 40 | 560000 | 0 | 0 | 560000 | 40 |  | 2013-11-01: 10; 2013-12-01: 3; 2014-01-01: 12; 2014-02-01: 5; 2014-03-01: 10 | CORRECT
219 | Corporate | Noor Islamic |  | G | AC | QMS |  | 30 |  |  |  |  | 30 |  | 2013-11-01: 10; 2013-12-01: 10; 2014-01-01: 10 | CORRECT
220 | Susmith | Integra Automation | 2013-2014 | G | I | QMS | Core Tools | 26 | 336000 | 13 | 168000 | 168000 | 13 |  | 2013-10-01: 2; 2013-12-01: 3; 2014-01-01: 2; 2014-02-01: 3; 2014-03-01: 3 | CORRECT
221 | Susmith | Takata India Pvt. Ltd | 2012-2013 | G | I | QMS | IQA TS/APQP | 8 | 112000 | 4 | 56000 | 56000 | 4 |  | 2013-11-01: 2; 2013-12-01: 2 | CORRECT
222 | Susmith | ELGI | 2013-06-01 | G | I | QMS | IA ISO 9001-2008/PFMEA/DFMEA | 24 | 288000 | 18 | 144000 | 144000 | 6 |  | 2013-10-01: 3; 2013-11-01: 3 | CORRECT
223 | Susmith | Yazaki Wiring Technology | 2013-02-01 | G | I | QMS | FMEA/IQA EMS/Core Tools | 8 | 100000 | 2 | 22000 | 78000 | 6 |  | 2013-10-01: 3; 2013-11-01: 3 | CORRECT
224 | Susmith | GKN Driveline | 2013-05-01 | G | I | QMS | Core Tools | 20 | 345000 | 15 | 153000 | 192000 | 6 |  | 2013-05-01: 2; 2013-10-01: 2; 2013-11-01: 2 | CORRECT
225 | Susmith | Yaap-Zoom Automotive | Before April | G | I | QMS | training | 3 | 140000 | 0 | 65000 | 75000 | 3 |  | 2013-11-01: 3 | CORRECT
226 | Susmith | Comstar Automotive Tech | 2013-05-01 | G | I | QMS | Core Tools | 12 | 112000 | 6 | 28000 | 84000 | 6 |  | 2013-05-01: 2; 2013-06-01: 2; 2013-08-01: 2 | CORRECT
227 | Susmith | Bimetal Bearings | 2013-11-01 | G | I | QMS | Core Tools | 13 | 182000 | 0 | 0 | 0 | 13 |  | 2013-09-01: 3; 2013-10-01: 2; 2013-11-01: 3; 2013-12-01: 2; 2014-01-01: 3 | CORRECT
228 | Susmith | Daimler | 2013-05-01 | G | I | QMS | Core Tools | 16 | 272000 | 6 | 170000 | 172000 | 10 |  | 2013-06-01: 2; 2013-07-01: 4; 2013-08-01: 4 | CORRECT
229 | Susmith | NBC Bearings | 2013-06-01 | G | I | QMS | Core Tools | 22 | 440000 | 22 | 440000 | 440000 | 22 |  | 2013-08-01: 5; 2013-09-01: 8; 2013-10-01: 2; 2013-12-01: 5; 2014-01-01: 2 | CORRECT
230 | Susmith | Western Thomson | 2013-09-01 | G | I | QMS | IQA/TS | 3 | 45000 | 0 | 0 | 0 | 3 |  | 2013-09-01: 3 | CORRECT
231 | Susmith | Henkel | 2013-10-01 | G | I | QMS | IQA/TS | 2 | 36000 | 0 | 0 | 0 | 2 |  | 2013-09-01: 2 | CORRECT
232 | Susmith | Brigestone | 2013-10-01 | G | I | QMS | Core tools | 9 | 144000 | 0 | 0 | 112000 | 7 |  | 2013-10-01: 2; 2013-12-01: 2; 2014-01-01: 3 | CORRECT
233 | Susmith | Infac India | 2013-10-01 | G | I | QMS | IQA/TS | 2 | 28000 | 0 | 0 | 28000 | 2 |  | 2013-10-01: 2 | CORRECT
234 | Susmith | Henkel | 2013-11-01 | G | I | QMS | IQA/TS+Audit | 4 | 48000 | 0 | 0 | 48000 | 4 |  | 2013-10-01: 4 | CORRECT
235 | Susmith | Daimler | 2013-10-01 | G | I | QMS | APQP/PPAP | 3 | 34000 | 0 | 0 | 34000 | 3 |  | 2013-10-01: 2; 2013-11-01: 1 | CORRECT
236 | Susmith | OET | 2013-10-01 | G | I | QMS | Core Tools | 5 | 115000 | 0 | 0 | 115000 | 5 |  | 2013-10-01: 5 | CORRECT
237 | Susmith | OET | 2013-11-01 | G | I | QMS | IQA/TS | 2 | 16000 | 0 | 0 | 16000 | 2 |  | 2013-11-01: 2 | CORRECT
238 | Susmith | Royal Enfield | 2013-11-01 | G | I | QMS | GD&T | 2 | 32000 | 0 | 0 | 32000 | 2 |  | 2013-11-01: 2 | CORRECT
239 | Susmith | Daimler | 2013-11-01 | G | I | QMS | TS Awareness Trg | 1 | 17000 | 0 | 0 | 17000 | 1 | [13 empty] | CORRECT | bar: 2013-11-01
240 | Susmith | Inzi Control | 2013-11-01 | G | I | QMS | PFMEA | 2 | 28000 | 0 | 0 | 28000 | 2 |  | 2013-11-01: 2 | CORRECT
241 | Susmith | Sanmina | 2013-11-01 | G | I | QMS | SPC | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-11-01: 2 | CORRECT
242 | Susmith | Sanmina | 2013-11-01 | G | I | QMS | FMEA | 2 | 30000 | 0 | 0 | 30000 | 2 |  | 2013-11-01: 2 | CORRECT
243 | Susmith | OET | 2013-11-01 | G | I | OET | Lead Auditor - IMS | 5 | 68000 | 0 | 0 | 68000 | 5 |  | 2013-11-01: 2; 2013-12-01: 3 | CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
CORRECT
[15 empty] | 266 | 276 | 282 | 267 | 305 | 381 | 307 | 379 | 322 | 287
Note on E1: Vijil: green: scheudled yellow: delayed Red: stopped
Note on F1: Vijil: inhouse-IH outsouce-Os Associate - AC
Note on I60: Vijil: 50:50 ac and consultnats
Note on I63: Vijil: SC:45 AC:15
Note on I65: Vijil: all senior, avijith can also do it
Note on I183: Rajan : 10 batches of 3 days
Note on K183: Rajan : 3 batches
Note on I184: Rajan : 2 days DFMEA 2 days EPS 2 days PFMEA 2 days Strenghening process

## total inv.
PERSONNEL | (All)
Values
Row Labels | Sum of Apr-13 | Sum of May-13 | Sum of Jun-13 | Sum of Jul-13 | Sum of Aug-13 | Sum of Sep-13 | Sum of Oct-13 | Sum of Nov-13 | Sum of Dec-13 | Sum of Jan-14 | Sum of Feb-14 | Sum of Mar-14
Bangalore |  |  | 3 | 5 | 5 | 14 | 7 | 3 | 17 | 12 | 21 | 15
Chennai | 46 | 43 | 44 | 14 | 29 | 37 | 43 | 61 | 21 | 18 | 15 | 6
Corporate | 150 | 169 | 164 | 134 | 140 | 163 | 77 | 54 | 46 | 48 | 33 | 28
Delhi | 36 | 18 | 23 | 35 | 49 | 47 | 36 | 34 | 33 | 13 | 5
Pune | 34 | 42 | 44 | 75 | 71 | 104 | 115 | 197 | 188 | 186 | 153 | 81
Susmith |  | 4 | 4 | 4 | 11 | 16 | 29 | 30 | 17 | 10 | 3 | 3
(blank)
Grand Total | 266 | 276 | 282 | 267 | 305 | 381 | 307 | 379 | 322 | 287 | 230 | 133

## client wise rqmt
PERSONNEL | (All)
Regions | (All)
Values
Row Labels | Sum of Apr-13 | Sum of May-13 | Sum of Jun-13 | Sum of Jul-13 | Sum of Aug-13 | Sum of Sep-13 | Sum of Oct-13 | Sum of Nov-13 | Sum of Dec-13 | Sum of Jan-14 | Sum of Feb-14 | Sum of Mar-14
AAM | 2 | 0 | 0
al-deer | [5 empty] | 2 |  | 2 | 3
ALP Nishikawa |  | 2 | [5 empty] | 2 | 2
ALP Nishikawa,Gurgaon |  |  |  | 1
ALP Nishikawa,Lalru |  |  |  | 2 |  |  |  | 2 | 0
ALP,Nishikawa-TQM | 2
Alpha | 2 | 2 | 3 |  | 2 | 2 | 4 | 3
AMTEK TEKFOR |  |  | 8 | 13 | 2
Amtek,Pune |  |  |  |  | 3 | 2 | 2
APPG - | [7 empty] | 3
Asahi | 4 | 0 | 2 | 0
Automotive Infotronics | 0 | 0
Bekart |  |  |  |  | 1 | 3 | 2 | 1
Bekart - july |  |  |  | 1 | 2 | 5 | 5 | 4 | 3 | 2 | 2
Bekeart | [5 empty] | 4
BGL,Faridabad |  | 2 | 2
Bhadve | 5 | 3 | 7 | 0 | 1
Bimetal Bearings | [5 empty] | 3 | 2 | 3 | 2 | 3
C P Acqua |  |  |  |  | 2
Caparo fasteners |  |  | 1
CM Smith foundry |  | 1 | 4 | 6 | 4 | 20
CM Smith Machine Shop | 4 | 3 | 6 | 8 | 2 | 2
Comstar Automotive Tech |  | 2 | 2 |  | 2
Continental Engines | 3 | 0 | 0 | 0 | 1
Daimler |  |  | 2 | 4 | 4 |  | 2 | 2
Danfoss | 3 | 0 |  |  |  | 0 | 0 | 0
Deccan Hydraulics | 2 | 1 | 2 | 0
Denso,Manesar |  |  |  | 0 | 5 | 2
Diamler |  |  | 2
DLMI | 8 | 16 | 10 | 10 | 14 | 13 | 4 | 6 | 5
Eco Cat,Faridabad |  | 3
Eco Cat-DOE | 2
Eicher |  |  |  |  | 2 | 1 | 3
Elforge | 3 | 2 | 4 | 0
ELGI | [6 empty] | 3 | 3
Ericsson,Jaipur |  |  |  | 0 | 3
Federal mogul | 2 |  |  |  |  | 2
Federal Mogul,Bhiwadi |  | 1 |  |  |  |  | 3
Flowmetalics |  |  | 6 | 2 |  | 2 | 2 | 2 | 2
Force motors | 0 | 0 | 0 | 0 |  | 4 | 4 | 9 | 9 | 9 | 9 | 9
Ford - STA -july | [6 empty] | 15
ford-thailand | [7 empty] | 15
Gilbarco | [6 empty] | 2 | 2
GKN Driveline |  | 2 |  |  |  |  | 2 | 2
Gokaldas Images-Enamor |  |  |  | 0 |  | 19 | 35 | 13 | 10 | 11 | 18 | 18
Grandpoly | 8 | 4 |  | 4 |  | 3 | 2 | 0 | 4 | 4 | 4 | 4
Groupo -july
Harsha Eng |  |  |  | 2
HEG LTD |  |  |  | 1
IAC |  | 0 | 0 | 0
IAI Joinflex | 2 | [5 empty] | 3 | 0 | 2 | 2 | 2
IMI Norgren | 0 | 1 | 0 | 2 | 1
INA | 0 | 3 | 7 | 6 | 7 | 6 | 4 | 4 | 8 | 8 | 8 | 8
Integra Automation | [6 empty] | 2 |  | 3 | 2 | 3 | 3
JBM | 3 | 1 | 3 | 0
JCB | 2 | 3 | 3 | 3 | 5 | 4 | 6 | 6 | 8
JCB,Faridabad |  | 2 | 1 |  |  |  |  | 2 | 2
JCB-DFMEA | 2
johndeere | 0 | 4 | 2 | 6 | 2 | 2
JSW |  |  |  | 2 | 2 | 8 | 7 | 3 | 8 | 10 | 11 | 13
JTEKT SONA |  |  | 2 | 2
Kalyani |  |  |  |  | 2
KFIL Audit |  |  |  |  | 4
klt - halol | 4 | 0 |  | 0 | 0 | 0 | 0 | 0
KLT - SA | 0 | 14 | 4
Lifelng,Haridwar | [6 empty] | 2 | 2
MACE | 2 |  | 2
Machino | 2 | 4 | 9 | 2
Maflow | 5 | 4 | 3 | 4 | 3 | 4 | 5 | 5 | 5 | 5 | 4 | 1
Magneti |  |  |  |  | 3
Mahindra composites | 2 | 2 | 6 | 6
Mahindra navistar |  | 6 |  |  |  |  | 4 | 4 | 4
Mahle,Gurgaon |  |  |  | 1 |  |  | 2
Mahle,Parwanoo |  |  |  |  | 2 | 4
Mate,Noida |  | 2 | 0 | 0 | 1
MSIL,Gurgaon |  |  |  | 0 | 4
NBC Bearings |  |  |  |  | 5 | 8 | 2 |  | 5 | 2
Neosem |  | 2 | 7 | 7 | 6
New Balance |  |  |  | 12 | 16 |  | 16
Nippon | 2 | 2 |  | 3 | 5 |  | 4 | 5 | 5 | 3 | 3
OET | 5 | 3 |  |  |  |  | 5 | 11 | 3
OET | [6 empty] | 2
OET - LAT |  |  |  |  | 5
Omax |  | 5 | 7 | 0 | 0 | 0 | 0
OMB Saleri | 2
Philps |  |  | 3
Poclain | 16 | 21 | 24 | 9 | 0 | 0 | 0 | 0
poclain ext cost
Raychem |  |  |  | 3 |  |  | 3 | 2 | 3 | 3 | 3 | 3
Rotex | 2 | 6 |  | 2 |  | 1 | 5 | 0 | 3 | 3 | 3 | 3
Salcomp | 2 | 3 | 3 | 0 | 5 | 3 | 2 | 3 | 3 | 5 | 3 | 3
Sanden Vikas |  |  | 1 | 1 | 1 | 2
Sanden Vikas,Faridabad |  |  |  |  | 2 | 2
SETCO |  |  | 4 | 12 | 2 | 12 | 21 | 13 | 15 | 15 | 15 | 15
SFL - pondy |  |  | 2 |  |  | 3 | 2 | 2
shankar | 10 | 7 |  | 5 | 2 | 4 | 15 | 15 | 15 | 15 | 10
shankarAC | 39 | 37 | 21 | 8 | 20 | 15 | 7
shriganesh Microsys | 3 | 2 | 1 | 5 | 2 | 4 | 0 | 2 | 2 | 4 | 4 | 2
Shriram Pistons,Biwadi | 0 | 0 | 3 | 3 | 4 | 4 | 1 | 1
Sigma Vibracoustiv | 0 | 0 | 0 | 0 | 2
SJP Ultrasonic |  |  |  | 3
SKF | 2 | [7 empty] | 2
Skoda | 67 | 76 | 68 | 68 | 96 | 123 | 21 | 25 | 19 | 19
SPM Autocomp,Pune | 7 | 1 | 0 | 0 | 2 | 4 | 1
ST MICRO,DFMEA | 2
STML Pondy
Subros,Manesar | [5 empty] | 3
Subros,Pune |  |  |  |  | 3 |  | 3
Supreme Ind |  |  | 1 |  |  |  |  | 4 | 4 | 4 | 4 | 4
Takata India Pvt. Ltd | [7 empty] | 2 | 2
Talbros,Faridabad |  |  | 0 | 2
Talbros,Gurgaon |  |  |  | 1
Tata Steel growth Shop | 0 | 0 | 0 | 0 | 0 | 2
Telleborg,Noida |  | 1
Titan | 3 | 0 | 2 | 4 | 7 | 4 | 2 | 2 | 2
TLC
TML ERC | 10 | 8 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 10 | 10 | 10
TML,Jamshedpur |  |  |  |  | 2 | 2
Treleborg,Noida | [5 empty] | 2
TTR |  | 4 | 7 | 2 | 1 | 2
Turbo energy july |  |  |  |  | 2
TVS Credit
Visteon |  |  |  | 3 | 2 | 7 | 5 | 2 | 2 | 2 | 2 | 2
Visteon
Visteon - |  |  |  |  | 1 | 2
Visteon climate | 10 |  | 4
Visteon Climate,System | 0 | 0 | 0 | 1 | 4 | 2 | 2
Visteon HVCC - | [6 empty] | 4 | 3 | 3 | 3 | 3 | 3
Visteon Tech
Visteonlss |  |  | 4 |  |  |  |  | 5 |  |  | 4
vistion electronics chennai | 3 | 0 |  |  |  | 3 | 0 | 3 | 3 | 3 | 3
vistion Interior chennai | 6 | 0 |  |  | 2 | 3 | 0 | 3 | 3 | 3 | 3
Yaap-Zoom Automotive | [7 empty] | 3
Yazaki Wiring Technology | [6 empty] | 3 | 3
Yengfeng Visteon |  |  |  |  | 2
Zavenir,Binola |  |  |  | 3
ZF | 1 | 8 | 4 | 6 | 3 | 3 | 6 | 2 | 2 | 6 | 2 | 2
Minda | [5 empty] | 2
Furecia | [5 empty] | 3 | 3 | 3 | 3
Mercedes |  |  |  | 2
Econ Packaging |  |  |  | 1
HYVA | [5 empty] | 3 | 3 | 3 | 2 | 3
Mate,Chennai | [5 empty] | 2
DR.Reddy Pathlabs,HYD |  |  |  |  | 2
Continental Auto, Manesr | [5 empty] | 2 | 2 | 2 | 2 | 2
TATA MARCOPOLO |  |  | 3 | 3 | 3 | 3 |  |  | 6 |  | 3
Larsen & toubro Ltd Mys | [9 empty] | 2 | 2
Panasonic Appliances | [5 empty] | 2 | 1
C P Aqua | [5 empty] | 1 | 2 | 2
Turbo Energy | [5 empty] | 1
CP Aqua | [5 empty] | 1
Minda corporatation | [6 empty] | 2
Lear | [6 empty] | 4
Excelcontrol | [7 empty] | 4 | 4 | 4 | 4 | 4
TML | [7 empty] | 45 | 40 | 40 | 40 | 12
FAG | [6 empty] | 4 | 2
Setco Uttarakhand | [6 empty] | 2 | 2 | 2
Hamdard Laboratories | [6 empty] | 4 | 6 | 6 | 4
Jtekt Sona, Bawal | [5 empty] | 2
Mate, | [5 empty] | 2 | 6 | 3
Subros,Noida | [8 empty] | 3
FESTO CONTROLS | [10 empty] | 5 | 2
FAURECIA | [8 empty] | 3
Inteva | [5 empty] | 3
Western Thomson | [5 empty] | 3
Henkel | [5 empty] | 2 | 4
Samarath | [6 empty] | 1 | 40 | 2 | 2 | 2 | 2
MPCB | [7 empty] | 10 | 40 | 40 | 30
Brigestone | [6 empty] | 2 |  | 2 | 3
Infac India | [6 empty] | 2
Royal Enfield | [7 empty] | 2
Accurate Products | [7 empty] | 3
Gilbarco Veedor - Mumbai | [7 empty] | 2
(blank)
Henkel,Chennai | [5 empty] | 2
Denso International | [7 empty] | 2
Woco Motherson,Noida | [6 empty] | 2 | 2
Shriram Pistons | [8 empty] | 4 | 4 | 5
Dr Reddy Laboratories | [8 empty] | 2
Siemens | [8 empty] | 3
Noor Islamic | [7 empty] | 20 | 13 | 22 | 5 | 10
Simpsons | [7 empty] | 1 | 1 | 2 | 1
MACE,Gurgaon | [7 empty] | 2 | 2 | 2
JCB,Pune | [8 empty] | 1
Jtekt Sona,Bawal | [7 empty] | 1
Mate,Chennai+Noida+Bangalore | [7 empty] | 1 | 1 | 1
Inzi Control | [7 empty] | 2
Sanmina | [7 empty] | 4
Grand Total | 266 | 276 | 282 | 267 | 305 | 381 | 307 | 379 | 322 | 287 | 230 | 133

## personnel inventory
| PERSONNEL | I
Values
| Row Labels | Sum of Apr-13 | Sum of May-13 | Sum of Jun-13 | Sum of Jul-13 | Sum of Aug-13 | Sum of Sep-13 | Sum of Oct-13 | Sum of Nov-13 | Sum of Dec-13 | Sum of Jan-14 | Sum of Feb-14 | Sum of Mar-14
| Bangalore |  |  | 3 | 5 | 5 | 14 | 7 | 3 | 17 | 12 | 21 | 15
| Chennai | 35 | 40 | 41 | 14 | 22 | 28 | 41 | 37 | 12 | 7 | 6 | 3
| Corporate | 44 | 56 | 75 | 50 | 34 | 45 | 39 | 33 | 31 | 33 | 30 | 28
| Delhi | 26 | 18 | 23 | 35 | 40 | 41 | 36 | 32 | 33 | 13 | 5
| Pune | 34 | 38 | 38 | 69 | 69 | 102 | 112 | 188 | 186 | 185 | 148 | 80
| Susmith |  | 4 | 4 | 4 | 11 | 16 | 29 | 30 | 17 | 10 | 3 | 3
| Grand Total | 139 | 156 | 184 | 177 | 181 | 246 | 264 | 323 | 296 | 260 | 213 | 129
ALLOCATED |  | 185 | 208 | 206 | 202 | 168 | 152 | 167 | 172 | 94 | 94 | 94 | 94
VARIANCE |  | -46 | -52 | -22 | -25 | 13 | 94 | 97 | 151 | 202 | 166 | 119 | 35
Cumulative |  |  | -98 | -120 | -145 | -132 | -38 | 59 | 210 | 412 | 578 | 697 | 732
| PERSONNEL | O
Values
| Row Labels | Sum of Apr-13 | Sum of May-13 | Sum of Jun-13 | Sum of Jul-13 | Sum of Aug-13 | Sum of Sep-13 | Sum of Oct-13 | Sum of Nov-13 | Sum of Dec-13 | Sum of Jan-14 | Sum of Feb-14 | Sum of Mar-14
| Chennai | 11 | 3 | 3 | 0 | 7 | 9 | 2 | 24 | 9 | 11 | 9 | 3
| Corporate |  |  |  | 8 | 16 | 3 | 20 | 5 | 5 | 4 | 3
| Delhi | 10 |  |  | 0 | 9 | 6 |  | 2
| Pune | 0 | 4 | 6 | 6 | 2 | 2 | 3 | 9 | 2 | 1 | 5 | 1
| Grand Total | 21 | 7 | 9 | 14 | 34 | 20 | 25 | 40 | 16 | 16 | 17 | 4
ALLOCATED |  | 17 | 7 | 9 | 8 | 16 | 9 | 16 | 0 | 94 | 94 | 94 | 94
VARIANCE |  | 4 | 149 | 175 | 169 | 165 | 237 | 248 | 323 | 202 | 166 | 119 | 35
Cumulative |  |  | 153 | 328 | 497 | 662 | 899 | 1147 | 1470 | 1672 | 1838 | 1957 | 1992
| PERSONNEL | AC
Values
| Row Labels | Sum of Apr-13 | Sum of May-13 | Sum of Jun-13 | Sum of Jul-13 | Sum of Aug-13 | Sum of Sep-13 | Sum of Oct-13 | Sum of Nov-13 | Sum of Dec-13 | Sum of Jan-14 | Sum of Feb-14 | Sum of Mar-14
| Corporate | 106 | 113 | 89 | 76 | 90 | 115 | 18 | 16 | 10 | 11
| Grand Total | 106 | 113 | 89 | 76 | 90 | 115 | 18 | 16 | 10 | 11
ALLOCATED |  | 106 | 113 | 89 | 99 | 90 | 105 | 105 | 129 | 94 | 94 | 94 | 94
VARIANCE |  | 33 | 43 | 95 | 78 | 91 | 141 | 159 | 194 | 202 | 166 | 119 | 35
Cumulative |  |  | 76 | 171 | 249 | 340 | 481 | 640 | 834 | 1036 | 1202 | 1321 | 1356
Particulars | Month | Inhouse | Outsourcing | AC
Chennai | April'13 | 35 | 11
Bangalore | April'13 | 0 | 0
Delhi | April'13 | 24 | 6
Pune | April'13 | 61 | 0
Susmith | April'13 | 0 | 0
Corporate | April'13 | 65 | 0 | 106
Chennai | May'13 | 40 | 3
Bangalore | May'13 | 10 | 0
Delhi | May'13 | 22 | 0
Pune | May'13 | 57 | 4
Susmith | May'13 | 4 | 0
Corporate | May'13 | 75 | 0 | 113
Chennai | June'13 | 39 | 3
Bangalore | June'13 | 3 | 0
Delhi | June'13 | 32 | 0
Pune | June'13 | 38 | 6
Susmith | June'13 | 8 | 0
Corporate | June'13 | 86 | 0 | 89
Chennai | July'13 | 21 | 2
Bangalore | July'13 | 10 | 0
Delhi | July'13 | 37 | 0
Pune | July'13 | 64 | 6
Susmith | July'13 | 4 | 0
Corporate | July'13 | 66 | 0 | 99
Chennai | Aug'13 | 22 | 7
Bangalore | Aug'13 | 5 | 0
Delhi | Aug'13 | 23 | 7
Pune | Aug'13 | 43 | 2
Susmith | Aug'13 | 17 | 0
Corporate | Aug'13 | 58 | 0 | 90
Chennai | Sep'13 | 10 | 0 | 0
Bangalore | Sep'13 | 11 | 0 | 0
Delhi | Sep'13 | 17 | 4 | 0
Pune | Sep'13 | 56 | 2 | 0
Susmith | Sep'13 | 13 | 0 | 0
Corporate | Sep'13 | 45 | 3 | 105
Chennai | Oct'13 | 9 | 6
Bangalore | Oct'13 | 7 | 0
Delhi | Oct'13 | 17 | 8
Pune | Oct'13 | 71 | 2
Susmith | Oct'13 | 15 | 0
Corporate | Oct'13 | 48 | 0 | 105
Chennai | Nov'13 | 27 | 0
Bangalore | Nov'13 | 3 | 0
Delhi | Nov'13 | 12 | 0
Pune | Nov'13 | 40 | 0
Susmith | Nov'13 | 11 | 0
Corporate | Nov'13 | 79 | 0 | 129
Note on C53: Sankar - 10 Volvo - 24 DLMI - 8 Skoda - 23
Note on E53: Sankar - 39 Skoda - 67
Note on C59: Sankar - 7 Volvo - 36 DLMI - 16 Skoda - 16
Note on E59: Sankar - 37 Skoda - 76
Note on C65: Volvo - 59 DLMI - 10 Skoda - 17
Note on E65: Sankar - 21 Skoda - 68
Note on C71: Sankar - 5 Volvo - 46 DLMI - 10 Skoda - 5
Note on E71: Sankar - 31 Skoda - 68
Note on C77: Sankar - 2 Volvo - 16 DLMI - 14 Skoda - 26
Note on E77: Sankar - 20 Skoda - 70
Note on C83: Sankar - 1 DLMI - 11 Gokaldas - 4 Skoda - 35
Note on E83: Sankar - 15 Skoda - 78 Gokaldas - 12
Note on C89: Sankar - 1 Gokaldas - 6 Skoda - 37 DLMI - 4
Note on E89: Sankar - 7 Skoda - 87 Gokalda - 11
Note on C95: Noor Islamic - 10 Gokal Das - 2 DLMI - 6 Skoda - 58 Gulf Jyothi - 3
Note on E95: Noor Islamic - 10 Gokaldas - 6 Sankar - 2 Skoda - 111

## PROJECT REVIEW
|  |  | Country | INDIA | PROJECT - MONTHLY PROGRESS REVIEW |  |  | 2013-11-01 |  |  |  |  | DATED:
|  | Project detail |  |  | Monthly project review template |  |  | STATUS |  |  | # DAYS |  | Plan vs actuals
Sl. | Region | Client | Project Title | Proj. Mgr | Updated? Y/N | Discussed in RM? (Y/N) | PPT Sent to Client ? (Y/N) | Project Status GYR | Project Start Date | Project end date | Budget Days | Billed Days | Billing/ Outstanding | # days rqmt | Comments
1 | Chennai | Titan Industries | BPR | Arun Thomas | Y |  | N | G | 25.10.2012 |  | 40 | 34 |  |  | On-going
2 | Chennai | visteon HVCC | TPM | Arun Thomas | Y |  | N | G | 17.10.2013 |  | 40 | 6 |  |  | On-going
3 | Chennai | Bekaert | ISO/TS 1649 Project | Arun Thomas | Y |  | N | G | 25.7.2013 |  | 24 | 11 |  |  | On-going
4 | West | INA Bearing | QMS Strenghtening | Imran Khan | Y | Y | Y | G | 2013-05-01 | 2013-11-01 | 39 | 39 |  | 0 | No actions required. Project Closed.
5 | West | Raychem RPG | Six Sigma Implementation | Imran Khan | Y | Y | N | R | 2012-02-01 | 2012-11-01 | 26 | 14 |  | 12 | Project restarted last month. First review completed.
6 | West | TML | EPS Training | Imran Khan | Y | Y | N | G | 2012-11-01 | 2013-12-01 | 150 | 86 |  | 64 | No trainings executed last month.
7 | West | Visteon Automotive | Training & Implementation Support | Vaibhav Gadhawe | Y | Y | N | G | 2013-08-01 | 2014-01-01 | 20 | 5 |  | 15 | No actions required.
8 | West | Shri Ganesh | TS Implementation | Vaibhav Gadhawe | Y | Y | N | R | 2012-12-01 | 2013-12-01 | 30 | 29 |  | 1 | Meeting with top Management need to be lined up for extension of man days. Revised plan to be made for this project. As per discussion an extension of 17 days to be taken from client.
9 | West | Nippon | QMS & EMS implementation | Vaibhav Gadhawe | Y | Y | Y | Y | 2013-02-01 | 2013-12-01 | 33 | 24 |  | 9 | Client is planning to go for Certification without concent of Omnex. Vaibhav to write a mail to client stating clearly the consequences.
10 | West | Moco & INC | QMS Implementation | Vaibhav Gadhawe | Y | Y | N | R | 2012-02-01 | 2012-11-01 | 18 | 18 |  | 0 | Project is on hold from the clients side due to internal problems.
11 | West | Maflow | TS Implementation | Vaibhav Gadhawe | Y | Y | Y | G | 2013-01-01 | 2014-02-01 | 30 | 22 |  | 8 | Primary escalation done to client to accelerate the procedures for design function. This may delay the certification process.
12 | West | Maflow | EMS Implementation | Vaibhav Gadhawe | Y | Y | N | G | 2013-01-01 | 2013-09-01 | 15 | 15 |  | 0 | Project closed.
13 | West | Excel Controlinkage | Training & Consulting Visits for TS | Vaibhav Gadhawe | Y | Y | N | Y | 2011-04-01 | Open contract | 50 | 32 |  | 18 | This contract is executed as per need of client.
14 | West | Setco | Training | Manish Dhanuka | Y | Y | N | G | 2013-06-01 | 2014-03-01 | 148 | 49 |  | 99 | Revised ppt to be followed. Maintenance, WCM module need to be prepared. Imran to discuss with Arun Sir regarding the same.
15 | West | Grand poly | TS Implementation | Manish Dhanuka | Y | Y | N | R | 2011-12-01 | 2014-03-01 | 55 | 35 |  | 20 | Project escalation done to top management. Need to have an one to one discussion to gain commitment from the team. The ppt needs to be updated as per revised plan.
16 | West | Rotex | TS Implementation | Manish Dhanuka | Y | Y | N | R | 2013-04-01 | 2014-03-01 | 49 | 9 |  | 40 | Project is on hold from the clients side due to internal problems. Need to get the confirmation for restarting the project.